## Variation Register
VARIATION REGISTER
Project: | [Project Name] |  | Date: | 2026-02-05
Client: | [Client Name]
Contract Ref: | [Ref]
Contract Type: | [NEC / JCT / FIDIC]
Currency: | GBP (£)
Prepared By: | [Your Company / QS]
Ref | Title | Description | Instruction Ref | Date Instructed | Originator | Status | Discipline | Location / Area | Quoted Value | Assessed Value | Agreed Value | Difference | Net Change | Cumulative | Type | In Valuation? | Val No. | Risk (1-10) | Time Impact | Notes
VAR-001 | Steelwork design change | Revised steel beam sizes to ground floor structure per RFI-045 | SI-001 | 2025-03-15 | Client | Agreed | Structural | Ground Floor | 50000 | 40000 | 42000 | -8000 | 42000 | 42000 | Add | Yes | 3 | 6 | No | Agreed at PM meeting 22/03
VAR-002 | Interior setting out revision | Amended partition layout to Level 2 offices following tenant confirmation | SI-002 | 2025-03-22 | Project Manager | Proposed | Internal Fit Out | Level 2 | 25000 | 15000 |  |  | 15000 | 57000 | Add | No |  | 4 | No | Awaiting QS assessment
VAR-003 | Lift procurement specification | Upgrade from 2nr to 3nr passenger lifts per revised fire strategy | IN-003 | 2025-04-01 | Contractor | Priced | Vertical Transport | Core | 600000 | 400000 |  |  | 400000 | 457000 | Add | No |  | 8 | 4 weeks | High risk — long lead item
VAR-004 | Drainage diversion | Divert existing foul drainage run discovered during excavation | SI-004 | 2025-04-10 | Engineer | Instructed | Civils | External | 85000 |  |  |  | 85000 | 542000 | Add | No |  | 5 | 2 weeks | Unforeseen ground conditions
VAR-005 | Omit roof terrace planters | Client instruction to remove roof terrace planting scheme | CI-005 | 2025-04-18 | Client | Agreed | Landscaping | Roof | -35000 | -35000 | -35000 | 0 | -35000 | 507000 | Omit | Yes | 3 | 2 | No | Credit confirmed
VAR-006 | Fire stopping upgrade | Additional fire stopping to service risers per building control comments | SI-006 | 2025-05-02 | Engineer | Proposed | Fire Protection | Risers | 120000 |  |  |  | 120000 | 627000 | Add | No |  | 7 | No | Provisional cost — survey needed
VAR-007 | External cladding colour change | Revised cladding colour from RAL 7016 to RAL 9005 per architect instruction | AI-007 | 2025-05-08 | Client | Priced | Facade | External | 18000 | 15000 |  |  | 15000 | 642000 | Add | No |  | 3 | No | No programme impact expected
VAR-008 | Additional power outlets | Extra double sockets to ground floor retail units (15nr additional) | SI-008 | 2025-05-15 | Client | Agreed | M&E | Ground Floor | 8500 | 7200 | 7500 | -1000 | 7500 | 649500 | Add | Yes | 4 | 1 | No
VAR-009 | Revised pile design | Additional piles required due to revised geotechnical report | SI-009 | 2025-05-20 | Engineer | Priced | Substructure | Foundations | 220000 | 195000 |  |  | 195000 | 844500 | Add | No |  | 9 | 3 weeks | Critical path item
VAR-010 | Omit feature staircase | Client value engineering — replace feature stair with standard | CI-010 | 2025-05-28 | Client | Agreed | Structural | Atrium | -95000 | -95000 | -92000 | 3000 | -92000 | 752500 | Omit | Yes | 4 | 1 | No | VE saving agreed
10 variations | [7 empty] | TOTALS | 996500 | 542200 | -77500 | -6000 | 752500

## Client View
VARIATION REGISTER — CLIENT VIEW
Project: | [Project Name]
Client: | [Client Name]
Date: | 2026-02-05
Ref | Title | Status | Agreed Value | Net Change | Cumulative | In Valuation? | Val No.
VAR-001 | Steelwork design change | Agreed | 42000 | 42000 | 42000 | Yes | 3
VAR-002 | Interior setting out revision | Proposed | 0 | 15000 | 57000 | No | 0
VAR-003 | Lift procurement specification | Priced | 0 | 400000 | 457000 | No | 0
VAR-004 | Drainage diversion | Instructed | 0 | 85000 | 542000 | No | 0
VAR-005 | Omit roof terrace planters | Agreed | -35000 | -35000 | 507000 | Yes | 3
VAR-006 | Fire stopping upgrade | Proposed | 0 | 120000 | 627000 | No | 0
VAR-007 | External cladding colour change | Priced | 0 | 15000 | 642000 | No | 0
VAR-008 | Additional power outlets | Agreed | 7500 | 7500 | 649500 | Yes | 4
VAR-009 | Revised pile design | Priced | 0 | 195000 | 844500 | No | 0
VAR-010 | Omit feature staircase | Agreed | -92000 | -92000 | 752500 | Yes | 4
|  | TOTALS | -77500 | 752500

## Summary
VARIATION SUMMARY
Project: | [Project Name]
Status | Count | Total Quoted | Total Agreed
Proposed | 2 | 145000 | 0
Instructed | 1 | 85000 | 0
Priced | 3 | 838000 | 0
Agreed | 4 | -71500 | -77500
Rejected | 0 | 0 | 0
Withdrawn | 0 | 0 | 0
TOTAL | 10 | 996500 | -77500

## How to Use
VARIATION REGISTER TEMPLATE
Getting Started
1. Update the project details in the header area (Project, Client, Contract Ref, etc.)
2. Delete the sample data rows and start entering your own variations
3. Use the Ref format VAR-001, VAR-002 etc. or your own numbering scheme
4. Status, Originator, Type, and In Valuation columns have dropdowns — click the cell to select
Sheets in this Template
Variation Register | Main working sheet — enter all variation data here
Client View | Stripped-back view for sharing with clients — auto-linked to the main register
Summary | Auto-calculated breakdown by status with totals
How to Use | This sheet — column guide and tips
Column Guide
Ref | Unique variation reference number
Title | Short descriptive title for the variation
Description | Detailed description of the change
Instruction Ref | Reference to the SI, AI, PMI, or CE that triggered the variation
Date Instructed | Date the variation was instructed or notified (DD/MM/YYYY)
Originator | Who raised it: Client, Engineer, Contractor, PM, or Cost Consultant (dropdown)
Status | Current status: Proposed → Instructed → Priced → Agreed (dropdown)
Discipline | Trade or discipline affected (e.g. Structural, M&E, Civils)
Location / Area | Where on site the variation applies
Quoted Value | Contractor's quoted price
Assessed Value | QS / Cost Consultant's assessed value
Agreed Value | Final agreed value (leave blank until agreed)
Difference | Auto-calculated: Agreed minus Quoted
Net Change | Auto-calculated: best available value (Agreed > Assessed > Quoted)
Cumulative | Auto-calculated: running total of Net Change
Type | Add (cost increase) or Omit (credit) (dropdown)
In Valuation? | Whether included in a payment valuation (dropdown)
Val No. | Which valuation number it was included in
Risk (1-10) | Risk score: 1-3 Low, 4-6 Medium, 7-10 High (validated)
Time Impact | Whether the variation affects the programme/schedule
Notes | Any additional notes, references, or comments
Tips
• Filters are enabled — use them to quickly find variations by status, originator, or discipline
• Difference, Net Change, and Cumulative columns calculate automatically
• The Client View sheet auto-updates from the main register — just print or export it
• Print in A3 Landscape for best results (already configured)
• Freeze panes keep headers visible when scrolling
Need more?
If you're outgrowing this spreadsheet, try ChangeLog — a purpose-built
variation register for construction teams. Multiple views, clean exports,
full audit trail, and team collaboration.
Visit: https://change-log.app